## Risk Summary
Risk Summary
Risk ID | Risk scenario | Risk score | Risk level | Risk level | Count
R-001 | Unapproved source change made with a stolen developer credential | 15 | High | Critical | 1
R-002 | Erroneous or harmful change introduced by a developer | 15 | High | High | 14
R-003 | Source control or CI pipeline tools unavailable during an urgent OT patch | 6 | Medium | Medium | 5
R-004 | Known-vulnerable dependency added to the build | 12 | High | Low | 0
R-005 | Malicious or typosquatted dependency or base image pulled into the build | 15 | High | Total | 20
R-006 | Source code made publicly available | 8 | Medium
R-007 | Unapproved change to the CI pipeline definition (poisoned pipeline execution) | 15 | High
R-008 | CI build agent compromised or persistent between jobs | 15 | High
R-009 | Secrets exfiltrated from the Secret Vault or CI jobs | 15 | High
R-010 | Image scanning bypassed or result ignored before publish | 12 | High
R-011 | SBOM or scan evidence altered inside the pipeline | 12 | High
R-012 | Signing key or signing step misused in CI | 10 | Medium
R-013 | Unauthorized or undefined IT→OT image promotion | 20 | Critical
R-014 | Site local storage tampered or poisoned | 10 | Medium
R-015 | Deploy controller compromised or over-privileged | 15 | High
R-016 | Workload deployed with privileged runtime settings | 15 | High
R-017 | Vulnerability disclosed after release goes undetected in OT | 16 | High
R-018 | Deployed pod moves laterally into OT cells | 15 | High
R-019 | Insufficient CI/CD audit logging | 12 | High
R-020 | Operations team insider misuses CI or vault administration | 10 | Medium

## Risk Assessment
CI/CD for OT – Risk Assessment
Focus: likelihood-driven risk assessment
Risk ID | Risk scenario | STRIDE category | MITRE TTPs | Threat scenario | Potential OT impact | Primary asset/process | Business priority | Likelihood rationale | Likelihood (1-5) | Impact (1-5) | Risk score | Risk level | Primary mitigation strategy | Action owner / notes | Diagram reference
R-001 | Unapproved source change made with a stolen developer credential | Spoofing / Tampering / Repudiation | T1078 Valid Accounts; T1528 Steal Application Access Token; T1195.002 Compromise Software Supply Chain | Using a stolen authentication token or session, an attacker pushes or merges code to source control (T01). | Malicious logic built and shipped to OT workloads as a trusted release. | Source Control | Critical | Developer tokens and sessions are frequently phished or leaked; one push can reach every site. | 3 | 5 | 15 | High | Phishing-resistant MFA, no long-lived PATs, signed commits, branch protection with 4-eyes review, SCM audit log to SIEM. | DevSecOps / IAM | AV01 · T01 → Source Control
R-002 | Erroneous or harmful change introduced by a developer | Tampering | N/A – unintentional (no adversary TTP) | A developer makes an erroneous or harmful change that is merged and released (T03). | Faulty application behaviour on the line; unplanned downtime or wrong process data. | Source Control | High | Human error is routine; impact depends on review and test depth. | 3 | 5 | 15 | High | Branch protection, pull requests with 4-eyes principle, CODEOWNERS on OT-critical paths, required unit/integration tests and SAST. | Development teams | AV02 · T03 → Source Control
R-003 | Source control or CI pipeline tools unavailable during an urgent OT patch | Denial of Service | T1499 Endpoint Denial of Service; T1498 Network Denial of Service | A DDoS or outage against central SCM/CI services prevents building and releasing a fix. | Unable to patch OT systems for the duration of the downtime; prolonged exposure to an active CVE. | Source Control / CI Pipeline | Medium | Running OT workloads do not depend on central CI, so only urgent changes are affected. | 2 | 3 | 6 | Medium | HA and backups for SCM/CI, documented break-glass build path, site keeps last approved releases for rollback. | Operations Team | Source Control / CI Pipeline
R-004 | Known-vulnerable dependency added to the build | Tampering | T1195.001 Compromise Software Dependencies and Development Tools | A dependency is upgraded or added at a version with a known vulnerability. | Exploitable component runs in OT workloads; possible remote code execution on the edge node. | Build Tool / SCA & SAST Scanner | High | Dependency drift is constant; likelihood is high without SCA gating. | 4 | 3 | 12 | High | SCA as a blocking gate with severity policy, lockfiles and pinned versions, dependency proxy, automated update PRs (Renovate/Dependabot). | DevSecOps | Build Tool → SCA & SAST Scanner
R-005 | Malicious or typosquatted dependency or base image pulled into the build | Tampering | T1195.001 Compromise Software Dependencies and Development Tools; T1204.003 Malicious Image | Build resolves a malicious public package, a dependency-confusion name, or a compromised base image. | Backdoor compiled into a released image and trusted by every OT site. | Build Tool / Image Builder | Critical | Supply-chain package attacks are frequent and bypass source review. | 3 | 5 | 15 | High | All packages and base images via Artifactory/Nexus proxy, namespace reservation for internal packages, approved base-image catalog, pinning by digest. | DevSecOps / Platform | Build Tool / Image Builder (no AV yet)
R-006 | Source code made publicly available | Information Disclosure | T1213.003 Data from Information Repositories: Code Repositories | Misconfiguration of project access or a leaked clone exposes source code. | Disclosure of OT endpoints, protocols, internal topology and possibly embedded credentials. | Source Control | Medium | Project visibility is inherited from organisation settings, which lowers likelihood. | 2 | 4 | 8 | Medium | Organisation-enforced private visibility, secret scanning with push protection, periodic access review. | DevSecOps | Source Control
R-007 | Unapproved change to the CI pipeline definition (poisoned pipeline execution) | Tampering / Elevation of Privilege | T1195.002 Compromise Software Supply Chain; T1078 Valid Accounts; T1059 Command and Scripting Interpreter | Using an authentication token, an attacker modifies the CI pipeline configuration or a shared library to skip gates or inject steps. | Security gates silently bypassed; malicious artifact produced with valid provenance. | CI Pipeline definitions | Critical | Pipeline files are often less protected than application code. | 3 | 5 | 15 | High | CODEOWNERS and 4-eyes on Jenkinsfile/pipeline paths, central versioned pipeline templates, no privileged jobs from PRs, OIDC workload identity. | DevSecOps / Operations Team | Operations Team → CI Pipeline (no AV yet)
R-008 | CI build agent compromised or persistent between jobs | Tampering / Elevation of Privilege | T1611 Escape to Host; T1525 Implant Internal Image; T1053 Scheduled Task/Job | Long-lived or shared runners, or an exposed docker.sock, let one job tamper with later builds. | Every image built on the agent can be backdoored; credentials on the agent stolen. | CI Pipeline runners | High | Shared, long-lived agents are common in Jenkins estates. | 3 | 5 | 15 | High | Ephemeral single-use agents, rootless image builds (Kaniko/BuildKit), no docker.sock, egress allow-list, separate pools per trust level. | Operations Team | CI Pipeline (no AV yet)
R-009 | Secrets exfiltrated from the Secret Vault or CI jobs | Information Disclosure / Elevation of Privilege | T1552 Unsecured Credentials; T1528 Steal Application Access Token | Attacker reads vault paths or CI environment and logs to obtain registry, signing or deployment credentials (T01). | Credentials enable image push, promotion or deployment to OT. | Secret Vault | Critical | Vault is a high-value target; CI jobs often over-scope secret access. | 3 | 5 | 15 | High | Short-lived dynamic secrets, per-pipeline least-privilege policies, log masking, vault audit to SIEM, rotation by Operations Team. | Operations Team / Security | AV04 · T01 → Secret Vault
R-010 | Image scanning bypassed or result ignored before publish | Tampering | T1685 Disable or Modify Tools; T1525 Implant Internal Image | Attacker or rushed operator publishes an image that skipped or failed scanning (T01). | Unscanned or vulnerable image is published and promoted to OT. | Image Scanning → publish | High | Gates are often advisory rather than blocking. | 3 | 4 | 12 | High | Blocking scan gate, publish only from the pipeline identity, signed scan attestation bound to digest. | DevSecOps | AV03 · T01 → Image Scanning / publish
R-011 | SBOM or scan evidence altered inside the pipeline | Tampering / Repudiation | T1525 Implant Internal Image; T1070 Indicator Removal | A pipeline step or operator changes the SBOM or scan report before it is attached to the image. | Unsafe image promoted with false assurance; weak incident evidence. | SBOM / Image Scanning | High | Evidence files are often plain artifacts with broad write access. | 3 | 4 | 12 | High | Generate SBOM from the built image digest, sign SBOM and scan results as attestations, restrict write access to the pipeline identity. | DevSecOps | SBOM / Image Scanning (no AV yet)
R-012 | Signing key or signing step misused in CI | Spoofing / Tampering | T1528 Steal Application Access Token; T1078 Valid Accounts | An attacker with pipeline or vault access signs an image that did not pass the gates. | Malicious image carries a valid signature and passes site verification. | Signing step / Secret Vault | Critical | Strong key protection lowers likelihood, but impact is severe. | 2 | 5 | 10 | Medium | Keys in KMS/HSM, signing only from the protected-branch pipeline identity after all gates, signing audit and anomaly alerts. | PKI / DevSecOps | CI Pipeline → Secret Vault (no signing step in diagram yet)
R-013 | Unauthorized or undefined IT→OT image promotion | Spoofing / Tampering / Repudiation | T1078 Valid Accounts | The release-manager promotion step is undefined; a compromised or mistaken account promotes an unapproved image. | Unapproved release staged for all sites; no evidence of who approved it. | Release Manager / promotion process | Critical | Process is marked unclear in the diagram; ad-hoc promotion is likely. | 4 | 5 | 20 | Critical | Define promotion gate: approved digests only, two-person approval tied to change ID, MFA, promotion via pipeline not manual push, recorded evidence. | Release Management | Release Manager → Image Registry
R-014 | Site local storage tampered or poisoned | Tampering | T1525 Implant Internal Image; T1070 Indicator Removal | Attacker with OT access alters cached images or manifests in local storage (T01). | Tampered workload runs at the site; rollback images may be corrupted. | Local Storage (Kubernetes) | High | Requires OT foothold; local caches are rarely integrity-checked. | 2 | 5 | 10 | Medium | Digest-only pulls, signature verification on every pod start, immutable storage, restricted write identity, integrity alerts. | OT Platform | AV07 · T01 → Local Storage
R-015 | Deploy controller compromised or over-privileged | Tampering / Elevation of Privilege | T1609 Container Administration Command; T1610 Deploy Container; T1078 Valid Accounts | Attacker takes over or re-points the deploy controller, which runs with broad cluster rights (T01). | Arbitrary workloads deployed across the site cluster; full cluster compromise. | Deploy Controller | Critical | Deploy controllers commonly run as cluster-admin. | 3 | 5 | 15 | High | Namespace-scoped service accounts, no cluster-admin, controller config under GitOps, signed desired state, deploy by digest, alert on config drift. | OT Platform | AV08 · T01 → Deploy Controller
R-016 | Workload deployed with privileged runtime settings | Elevation of Privilege | T1610 Deploy Container; T1611 Escape to Host | A manifest requests privileged mode, hostPath, host networking or extra capabilities and is applied unchecked. | Container escape to the OT edge node; access to node credentials and networks. | Deploy Controller → Deployed Pod | High | Common in vendor charts and quick fixes. | 3 | 5 | 15 | High | Admission control with Pod Security restricted, non-root, read-only root filesystem, drop capabilities, policy checks in CI on manifests. | OT Platform | Deploy Controller → Deployed Pod
R-017 | Vulnerability disclosed after release goes undetected in OT | Elevation of Privilege / Information Disclosure | T1190 Exploit Public-Facing Application; T1068 Exploitation for Privilege Escalation | A CVE is published for a component in an already-released, deployed image; no re-scan occurs. | Exploitable workload keeps running in OT with no alert. | Deployed Pod / released images | High | New CVEs appear weekly for common base images. | 4 | 4 | 16 | High | Continuous re-scan of released images against SBOMs, revocation signal for affected releases, site notification and patch SLA. | DevSecOps / SOC | Image Scanning → Deployed Pod
R-018 | Deployed pod moves laterally into OT cells | Elevation of Privilege / Information Disclosure | T1611 Escape to Host; T1550 Use Alternate Authentication Material; T1046 Network Service Discovery | A compromised pod scans and reaches PLC/HMI networks or other namespaces. | Manipulation of OT process; safety and production impact. | Deployed Pod → OT cells | Critical | Runtime blast radius is not modelled in the diagram yet. | 3 | 5 | 15 | High | Default-deny NetworkPolicy, egress allow-list to named OT assets and protocols, Pod Security restricted, OT firewall between cluster and cells. | OT Platform / OT Security | Deployed Pod → OT (no AV yet)
R-019 | Insufficient CI/CD audit logging | Repudiation | T1070 Indicator Removal | SCM, CI, vault, promotion and deployment actions are not logged centrally or retained. | Cannot prove who changed, built, promoted or deployed a release; slow incident response. | CI Pipeline / Source Control / Deploy Controller | Medium | Logging gaps are common across tool chains. | 3 | 4 | 12 | High | Forward SCM, CI, vault, promotion and deploy logs to SIEM, append-only retention, coverage review against this register. | SOC | CI Pipeline / Source Control
R-020 | Operations team insider misuses CI or vault administration | Tampering / Repudiation / Elevation of Privilege | T1078 Valid Accounts; T1098 Account Manipulation | An authorized operator alters jobs, grants rights or reads secrets beyond need (T02). | Gates disabled or credentials exposed with legitimate access, hard to detect. | CI Pipeline / Secret Vault | High | Admin roles are broad and rarely separated. | 2 | 5 | 10 | Medium | Separation of duties, JIT admin access, MFA, admin action alerts, quarterly access review. | Security / Operations Team | Operations Team → CI Pipeline / Secret Vault

## Mitigation Roadmap
Phase | Priority | Mitigation focus | Related risks | Expected likelihood effect
Phase 1 | Critical | MFA and no long-lived tokens; branch protection with 4-eyes and CODEOWNERS on code and pipeline paths; central pipeline templates; defined two-person IT→OT promotion gate; signing only after all gates with keys in KMS/HSM; namespace-scoped deploy controller with signed desired state. | R-001, R-002, R-007, R-012, R-013, R-015, R-020 | Reduces likelihood of unapproved source, pipeline or promotion changes and of a validly signed malicious image.
Phase 2 | High | Dependency proxy and pinning; SCA, SAST and image scanning as blocking gates; SBOM from the built image; signed scan and SBOM attestations; ephemeral rootless build agents; dynamic secrets from Vault. | R-004, R-005, R-008, R-009, R-010, R-011 | Reduces likelihood of supply-chain injection, unscanned images, tampered evidence and secret theft.
Phase 3 | High | Admission control at site (signature and Pod Security restricted); digest-only pulls; default-deny network policy and egress allow-list to OT cells; integrity checks on local storage. | R-014, R-015, R-016, R-018 | Reduces likelihood that a malicious or misconfigured workload compromises the node, cluster or OT cells.
Phase 4 | Medium/High | Central immutable logging for SCM, CI, vault, promotion and deployment; continuous re-scan and release revocation; SCM/CI availability and break-glass path; source visibility controls. | R-003, R-006, R-017, R-019 | Reduces likelihood of unnoticed pipeline abuse and stale vulnerable releases; shortens response time.

## Scoring Model
Likelihood Scale
Score | Likelihood | Definition
1 | Rare | Highly unlikely; requires multiple control failures or unusual access.
2 | Unlikely | Possible but not expected; limited opportunity or compensating controls.
3 | Possible | Credible scenario; plausible in CI/CD and registry workflows.
4 | Likely | Expected under realistic attack conditions where controls are weak.
5 | Almost Certain | Highly probable without strong controls.
Impact Scale
Score | Impact | Definition
1 | Negligible | Minimal effect.
2 | Minor | Limited issue; short recovery.
3 | Moderate | Degraded OT security visibility or contained exposure.
4 | Major | Material OT monitoring blind spot or significant response impact.
5 | Severe | Persistent compromise or serious loss of trust.
Risk Level Thresholds
Score range | Risk level | Suggested response
1-5 | Low | Accept/monitor.
6-11 | Medium | Assign owner and mitigation plan.
12-19 | High | Prioritize mitigation and review.
20-25 | Critical | Immediate action or block path.

## Source Notes
Source diagram | CI/CD for OT and IT threat model diagram (original version: IT CI pipeline, DMZ, Factory/OTPM Kubernetes; attack vectors AV01–AV08; threat agents T01–T03)
Scope | CI/CD project only: source control, CI pipeline, secrets use, signing, IT→OT promotion, site deploy controller, local storage and deployed workloads. Each project delivers its own threat model and risk assessment.
Out of scope | Image registries (IT and DMZ) and the IT→DMZ replication path belong to the Trusted Registries project. Diagram vectors AV05 and AV06 are covered there; this pipeline depends on those controls.
Scoring formula | Risk score = likelihood x impact.
Scores and owners | Likelihood, impact and action owners are proposals for stakeholder review.
Diagram reference | Links each risk to its attack vector (AVxx) and component. Rows marked 'no AV yet' are gaps to add to the diagram.
MITRE TTPs | MITRE ATT&CK Enterprise v20. CI/CD supply-chain techniques (T1195, T1213, T1059) come from the full Enterprise matrix, not the Containers view.
Threat agents | T01 Unauthorized user · T02 Authorized user · T03 Developer (as in the diagram).